Project Plan for Catalyst Proposal #1100249

Project Title: Adaptation of Catalyst Ecosystem to Decentralized Governance through the Council System

Duration: 12 months (5 Months for due date)

Project’s Main Objective:

The objective of this research project is to contribute to develop a decentralized governance system for the Catalyst ecosystem by adapting Hannah Arendt’s concepts of the Governance philosophy for decentralised power. Such task seeks to provide a comprehensive framework for decentralised governance (human driven) for Cardano’s Catalyst by capturing the core features or foundational characteristic for which governance in decentralised systems is differentiated from traditional systems.

Milestone 1: (already submitted)

Milestone 2 Plan: In-depth Research and Framework Development

Objective: Conduct in-depth research on the Catalyst ecosystem and develop a comprehensive framework for the integration of Hannah Arendt's Council System into Catalyst.

Key Tasks:

- Extending from the preliminary research conducted in Milestone 1 and by including new literature, denote specific functional and core procedures on governance extracted from Hannah Arendt’s council system.

- Study the operational mechanisms within the Catalyst ecosystem’s current governance and highlight the opportunities for the council system implementation.

Analysis of Catalyst’s Current Governance:

Catalyst System Overview: Examine the participatory structures in place within Catalyst and identify potential gaps where the Council System could improve or replace existing processes.

Comparison with Council System: Compare and contrast Catalyst's governance with Arendt’s principles, identifying overlaps and discrepancies in political freedom, participation, and decentralization.

Framework Development for HACS Implementation:

Building the Framework: Revised in milestone 1, from the main works of Hannah Arendt, create a guide in the most practical manner on how the council system can be introduced into Catalyst. For this, categories of governance that have been identified from Arendt’s main work need to be structed, defined and adapted. This should include actionable recommendations highlighting the logic for this decentralised decision-making.

Addressing Challenges: Identify challenges that might arise from this integration and propose potential solutions based on historical implementations of similar systems (drawing from US, French, Hungarian, and Russian decentralized systems).

Outputs:

In-depth Research Document: A comprehensive analysis of Catalyst’s ecosystem.

Implementation Framework for the council system: A clear, actionable framework that outlines how HACS can be introduced, along with the benefits it brings to Catalyst’s governance model.

Plan to develop the concepts Identified so far for further research and Method of research:

Arendt’s work point to several moments in history before the main democratic constitutions were created, she explores a governance process that repeats in history, which is short-lived and for which the initial intention is intuitively the creation of a system of equal humans that has axiomatically sustained governance of decentralised power. Such intentions had objectives considerable similar but failed to be materialised, moreover becoming the main dominance governance systems in the current international scenario, democracy and communism. Both in their early days and in their different places of revolution systematically discarded the idea of a polis were all the citizens enjoy equal political rights.  To explore these concepts the main Arendt’s text will be used to further pinpoint her critics on centralisation then identifying her proposed solutions to find conceptual dead ends. Such conceptual dead-ends are also depicted in the conceptual map for this reason I see no need to include in this plan. Nonetheless the method for the conceptual exploration and process to make these practical, requires that after this conceptual “dead-ends” are identified, defined and discussed. There will be problems identified ample enough to provide solutions as proposition using AI tools, the revision of social sciences’ journals (sociology, philosophy etc.) and the consultation with other academics with interest on Arendtian ideas. So far, the ideas identified as core concepts can be seen in the main conceptual map and literature review along their main arguments and corresponding literature citation.

1. Arendt’s Critic of democracy: There has been already extensive scholarly literature on the concepts that Arendt presents as critics for the conventional democratic systems. For this reason, there will be a brief remark that will summarise (without going in depth) such critics.

2. The modus of deliberation for de council system: This core subject intends to rescue Arendt’s conceptual and philosophical remarks on anything that relates to deliberation. This is one of the most important subjects to explore because it does imply that there must be a methodology that will secure a lasting power decentralisation in governance that has not being implemented to the date.

3. The meaning of freedom in the council system: Arend’t philosophy is based on a specific conception of freedom. Such conception is a precondition that needs to be secured and fulfilled by the system in order to maintain power decentralised.

4. The meaning of the political in the council system: Just as the concept of freedom, Arendt denotes the political as different to the conventional meaning and a condition a priori for the implementation of decentralised governance. Moreover, such meaning of “the political” cannot be detached for what she also defines as “the social” which is another concept as sophisticated as “the political” in Arendtian thought.

5. The formation of power in the council system: The system indeed requires power to be commended. It is not yet clear how power is distributed institutionally. Nonetheless, power in Arendt’s works has a defined ontology and under the council system is throughout dialogue that power (as well as truth) is becoming “common knowledge” (another Arendtian concept in itself). This concept alone is the most challenging given that it does need to be clarified what is the process to achieve this decentralisation of power and not just to know the dynamic in which power is created in a decentralised fashion.

6. The historical justification of the council system (Decentralisation and revolutions in US, French, Hungarian and Russian history): This is precisely the main contribution attributed to Arendt, it has been identified that decentralisation of power has happened in all these main revolutions and that such “equal-power-for-all” situation has been always short-lived. Going to this core concept is primordial as there are not many revisions on the subject. Yet the proposition of Arendt is not to suggest that the condition of decentralised power is an ideal system although it seems to be intuitively fairer, with its own challenges and by no means a utopian model.

7. Finding the minimum imperative for the structure of a decentralised system: This subject intent to stablish an initial enquiry on those unavoidable features that the nature of a decentralised power system should have and therefore those concepts that should be contemplated in its constitution.

Acceptance Criteria:

The research document thoroughly analyses governance structures and participation mechanisms within Catalyst.

The framework is actionable, addresses potential challenges, and provides clear implementation steps.

Milestone 3 plan: Initial Feedback

Objective: Collect and incorporate feedback from experts and peers on the proposed framework and research findings.

Key Tasks:

Peer Review and Expert Feedback:

Feedback Collection: Engage with governance scholars, political theorists, and Catalyst stakeholders to review the research and framework.

Feedback Log: Document all feedback, categorizing it into thematic areas (e.g., implementation challenges, conceptual clarity, governance alignment).

Revisions Based on Feedback:

Framework Adjustment: Revise the HACS framework based on expert and peer suggestions, ensuring alignment with the practical and theoretical insights.

Incorporation of New Ideas: Include new concepts from governance experts on decentralized systems that enhance the robustness of the framework.

Outputs:

Summary of Feedback: A log of all feedback received and how it was incorporated.

Revised Framework: An updated version of the HACS implementation framework based on feedback.

In order to make the feedback easy to revise, I will consult with a local scholar that has at least done some research on Hannah Arendt’s works, (someone located in Australia preferable).  There is a list of potential candidates including Ned Curthoys, Margarite La Caze and Daniel Brennan. Thes person or persons should read the work done so far, and the revision will be done in a conversation manner via Zoom or other digital medium to have a recorded version of the feedback discussion. Given that the price of ada is below 50% compared to the time the proposal was made, not many academics will be consulted as these need to be rewarded for their contribution and acknowledged. Prior the feedback encounter, the literature of the academic will be revised in order to find better points of discussion.

Acceptance Criteria:

Feedback is documented and revisions are clearly articulated.

(Documentation will be the recording of the feedback and the updated document as evidence)

Suggestions from academics and Catalyst stakeholders are incorporated into the draft.

(a consultation with someone in competence to contribute from Catalyst is yet to be stablished)

Milestone 4: Final Drafting

Objective: Develop a comprehensive and well-structured final draft of the research paper that incorporates all findings and framework details.

Key Tasks:

Consolidating Research and Findings:

Synthesizing Insights: Gather all the findings from previous research, the revised framework, and feedback from Milestone 3 to create a cohesive narrative.

Theoretical Integration: Integrate Hannah Arendt’s philosophical underpinnings with the practical requirements of the Catalyst ecosystem, ensuring the council system aligns with Catalyst’s decentralized governance model.

Drafting the Research Paper:

Structure: Organize the paper into clear sections: introduction, literature review, Catalyst ecosystem analysis, HACS framework, challenges, and solutions.

Incorporation of Feedback: Ensure the draft reflects the feedback from governance experts and addresses any outstanding concerns from earlier stages.

Under the subject of “political theory” or “decentralised governance” The potential Journals for publication of the research will be the following (unless better fit):

Ensuring Compliance with Acceptance Criteria:

Review the draft to ensure it aligns with the milestone’s acceptance criteria, particularly in terms of structure, clarity, and the thoroughness of the research.

(These requirements will also fit with the Journal requirements)

Outputs:

Final Draft of the Research Paper: A complete draft ready for professional editing, including all research findings and detailed framework discussions.

Under the subject of “political theory” or “decentralised governance” The potential Journals for publication of the research will be the following (unless better fit), the places of Publication will be intended in the following order:

SAGE Open (https://journals.sagepub.com/home/sgo)

PLOS ONE (https://journals.plos.org/plosone/)

Frontiers in Political Science (https://www.frontiersin.org/journals/political-science)

MDPI - Social Sciences (https://www.mdpi.com/journal/socsci)

Cogent Social Sciences (https://www.cogentoa.com/journal/social-sciences)

Heliyon (https://www.cell.com/heliyon/home)

Acceptance Criteria:

The draft is comprehensive and well-structured.

All research findings and framework details are clearly articulated, meeting the acceptance standards for a final submission.

Final Milestone: Final Output and Dissemination

Objective: Finalize the research paper, submit it to a journal, and disseminate the findings to the community.

Key Tasks:

Editing and Proofreading: Professionally edit and proofread the final draft to ensure it is publication ready.

Submission to Journal: Identify appropriate open-access journals focusing on political theory, decentralized governance, or digital ecosystems, and submit the paper.

Dissemination of Findings:

Community Engagement: Organize community engagement events (e.g., webinars, presentations) to discuss the findings and gather feedback from the Catalyst and wider academic community.

Dissemination Report: Document outreach activities, including participant numbers, engagement statistics, and key takeaways from the discussions.

Project Closeout:

Closeout Report: Summarize the project’s achievements, challenges, and future recommendations.

Project Closeout Video: Produce a video summarizing the project’s goals, research findings, and impact on Catalyst’s governance.

Outputs:

Finalized Research Paper: Submitted for publication.

Dissemination Report: A report on outreach activities and community engagement.

Project Closeout Report and Video: Summarizing project outcomes and future recommendations.

The receive for successful submission or awaiting correction/submission will be presented.

Besides the Catalyst requirements, it will be intended to have an initial point of dissemination in the Catalyst Townhall. Nonetheless, to make an efficient dissemination of the results, it will be important to make a series of videos explain in most possible detail, the main subjects of the research, and upload those videos in YouTube. In addition, if the community is interested it will be proposed a Q&A in demand.

Acceptance Criteria:

Proof of submission to a suitable journal.

Evidence of dissemination activities and community engagement.

Project Closeout Report and Video.